## Project
Project Overview
PE Owners (If Applicable): | JMAN - PE
Client | JMAN - Client
Project Code: | JMCLI_001
Project Name: | <Project name>
Client Informations
Client Name | JMAN - Client
Business
Requirements
Features
Estimated Time | 1 week
Deliverables
Technical Approach | Requests , Playwright(Backup approach)
Scope
Additional Costs
Potential Blockers | Cloudflare, Rate Limit
Mitigation Plan | Utilzing the Playwright based approach
Achievements
Total websites | Easy to scrape | Moderate | Hard
5 | 3 | 1 | 1
Resourcing
For the Data extraction will be required below expertise
3 X Data Engineer | 100 FTE %
API cost & IP cost
| Cost | account count | Comment
Alternate Sources
dataplor (€0.08 / record) | Global Quick Service Restaurant Location Data ¦ 100K+ Businesses ¦ 250 Countries & Territories ¦ Supply Chain ¦ Site Selection ¦ Datarade
Plugindata (€0.10 / record) | Restaurant Database Worldwide: 4M+ Restaurants, bars and cafes from 240 Countries, Expansion Opportunities ¦ Datarade
Using serpAPI or google API to fetch restaurant data from Search Engines
Using serpAPI or google maps API or OpenStreetMaps API to fetch restaurant data from Map Apps

## Web Scraping Feasibility
Feasibility Analysis
Note: | This template helps with conducting feasibility checks and identifying blockers for web scraping projects on websites.
# | Site Name | URL | Credentials | Tech | Method | Run Time Test(1 hit) | Run Time Test(100 hits) | Has Blockers? | Blockers | Proxy Required? | VM Required? | Total of data(No) | Build Scrapper Time(hours) approx* | Difficulty level | Estimate Days to extract all Data | Owner | Mitigation Plan
1 | Keywords Studios | https://www.vmc.com/ -> (https://www.keywordsstudios.com/) | None | Python | Selenium | 0.99 (Only Hit is Considered) | 92.05 | Y | SSL Handshake Error | N | N | Not Estimated | 1.5 | Moderate | Not Estimated | Chandravel MK | Use Selenium for Further Scraping
2 | Invest Conseil | https://www.invest-conseil.be/ | None | Python | Request | 8.17 | 541.67 | N | - | N | N | Not Estimated | 1 | Easy | Not Estimated | Chandravel MK | -
3 | Bureau Gilquin | https://bureaugilquin.be/ | None | Python | Request | 3.49 | 153.56 | N | - | N | N | Not Estimated | 1 | Easy | Not Estimated | Chandravel MK | -
4 | Van Renterghem & Co NV | https://www.vanrenterghemenco.be/ | None | Python | Selenium | Not Performed | Not Performed | Y | SOPHOS Blocker | N | N | Not Estimated | 1.5 | Hard | Not Estimated | Chandravel MK | Use Private Network
5 | VF Corporation | https://vfc.com/ | None | Python | Request | 1.04 | 92.44 | N | - | N | N | Not Estimated | 1 | Easy | Not Estimated | Chandravel MK | -

## Datapoints
Data Points
Note: | Identifying and collecting essential data points (fields) from websites
# | Websites | Datapoints
1 | Just Eat - Italy | Restaurants name
Restaurants Id
Restaurants unique name
Restaurants address
Restaurants rating
Restaurants timings
Restaurants cuisines
Restaurants availability
Restaurants ETA
2 | Deliveroo - italy | Restaurants name
Restaurants ETA
Restaurants rating
Restaurants min cost
Restaurants cuisines
Restaurants menu
Restaurants timings
Restaurants address
3 | Glovo - Italy | Restaurants name
Restaurants ETA
Restaurants rating
Restaurants offers
Restaurants Contact
Restaurants service cost
Restaurants cuisines
Restaurants menu
Restaurants timings
Restaurants address
4 | DoorDash - USA | Restaurants name
Restaurants ETA
Restaurants rating
Restaurants offers
Restaurants Contact
Restaurants cuisines
Restaurants menu
Restaurants timings
Restaurants address
5 | Uber Eats - USA | Restaurants name
Restaurants Id
Restaurants ETA
Restaurants Location
Restaurants timings
Restaurants description
Restaurants service cost
Restaurants menu
6 | GrubHub - USA | Restaurants name
Restaurants Id
Restaurants delivery fee
Restaurants min cost
Restaurants Contact
Restaurants offers
Restaurants ETA
Restaurants rating
Restaurants cuisines
Restaurants menu
Restaurants timings
Restaurants address

## Lookup (hidden)
IP Blocker | Easy
Captcha | Moderate
Press & Hold Button | Hard
Others